## Slide 1
2359BC02-6838-4D94-8CAC-4C1A9F4A54D8
Migration Plan
Prepared for: Contoso
Complete Scope

## Slide 2
1504FF82-CD05-4256-8D72-BA7626A85901
WHAT'S COVERED
Migration Plan - From Assessment to Execution
End-to-end migration plan: estate insights, strategy decisions, and delivery roadmap
DISCOVERY
STRATEGY
EXECUTION
Discovery & Scope
Migration Decisions
Execution & Delivery
Executive Overview
6R Strategy Allocation
App Complexity Profile
Environment Profile
Cloud Targets
Wave Plan Overview
Cost Overview
Risk Management
Next Steps
Appendix
Note: Each page includes a navigation breadcrumbs showing where to access live insights in Dr Migrate.
>
Migration Planning
>
Migration Treatment

## Slide 3
CFF6A9FC-F8B8-43BC-8137-7899F8671051
EXECUTIVE OVERVIEW
Migration Plan Overview
Assessment complete - environment profiled, treatments assigned, cost model validated, initial wave plans defined.

## Slide 4
9A02A9F0-3090-4EA7-8513-BDC0C47DEC7A
FINANCIALS
Cost Overview & Savings Drivers
Total cost of ownership analysis with savings broken down by driver - rightsizing, modernization, and licensing optimization.

## Slide 5
BA7B1DCC-572A-4036-A711-C4E8E7CA963F
FINANCIALS
Cost Comparisons - by Service Tiers
A line-by-line comparison of current and future-state annual cost across each infrastructure domain, showing where migration reduces spend and where it adds.

## Slide 6
2B846F6B-DE05-4B54-AB0C-6BBB23939D79
FINANCIALS
Cost Comparisons - Visualized
Side-by-side comparison of current vs future state cost by category.

## Slide 7
47DFC068-CB45-406A-9ABA-E9E43F90263A
TCO Analysis
>
Scenario Based
>
Rehost All
>
Optimize Impact
Server Optimization & Savings
Rightsizing analysis for the servers targeted at rehost, matching compute and memory allocation to actual utilization to lower ongoing run cost.

## Slide 8
B316F0D1-65F5-49C4-8722-4A1F27ED56ED
TCO Analysis
>
TCO Settings
Key Cost Modeling Configuration Applied
Cost Model Configuration
The financial insights in this report define how cloud costs, optimization opportunities and financial outcomes have been modelled throughout this report.
You're in Control Every assumption in this report is fully configurable in Dr Migrate. Update pricing, optimization preferences and deployment assumptions to instantly regenerate financial models.
Estimated using industry benchmarks and workload assumptions. Update these values in Dr Migrate to model your own environment.

## Slide 9
3ED903B4-1806-405F-8B34-122ED1D0935B
Current Environment Baseline
A clear view of your infrastructure, application estate, and technology risks - forming the foundation for migration and modernization decisions

## Slide 10
072A9C48-08E1-4630-8541-61CCC4A18002
Estate Explorer
>
Overview
Your Estate Overview
This snapshot summarizes the size, health, risks, and modernization opportunities across your environment.

## Slide 11
16E99298-2BE6-4F4D-9BFC-A3C0F8CE0F6D
Workload Mapping
>
Auto-Detect
Application Portfolio
Your environment has been catalogued across key technology domains using a combination of our pattern recognition engine and any user-supplied application mappings. These detected technologies form the foundation for assessing modernization opportunities, migration suitability, and potential risks throughout this report.

## Slide 12
4CF01F4E-DCFB-452B-95F5-DEF0C62F78C6
Estate Explorer
>
Technologies
Technology Domains Analyzed
Technologies discovered across your environment have been grouped into logical domains to simplify analysis, identify trends, and prioritize modernization opportunities. These domains form the foundation for the modernization and risk insights presented throughout this report.

## Slide 13
F1A0DE5A-9BEE-45CC-9C95-704174C58D8C
Migration Decisions & Outcomes
Defining the right migration approach for each application â€” from 6R classification to technology platform decisions.

## Slide 14
B9055F2E-1F89-4D0F-A779-30076512275D
Migration Treatment Strategy
Applications have been assessed and assigned to their recommended 6R migration treatment based on business, technical, and modernization considerations.

## Slide 15
9A802915-A666-460A-BA2D-9D65923188E0
Target Cloud Services
The following cloud platforms and managed services represent the recommended future-state architecture. Selected based on the migration treatments and modernization strategy, they highlight the expected consolidation benefits and reduction in infrastructure footprint.

## Slide 16
7D162BE9-A647-4DA2-89D6-D0C64ADFE07A
End-of-Life Technology Overview
Technologies approaching or beyond vendor support have been identified across the environment. This view highlights modernization progress and the remaining technology risk to help prioritize remediation and migration activities.

## Slide 17
B4D62671-05A0-4EAE-89B7-41BB7E2B3343
TCO Analysis
>
Scenarios
SQL Hosting & Modernization
Compare the projected annual cost, licensing impact, and operational benefits of each Azure SQL migration pathway to identify the best fit for your environment.

## Slide 18
3A022B37-6FE1-4BAD-ACDD-B62588EB7929
Execution
Translate migration strategy into an executable delivery plan.

## Slide 19
AC39B1D2-71F9-459A-9764-8A0D8DD0A118
Estate Explorer
>
Modernization
>
Cloud Readiness
Rehost Migration Readiness
Applications and servers assigned to the Rehost treatment have been assessed for immediate migration readiness. This view identifies workloads that are ready to migrate, those requiring remediation, and those needing further assessment before deployment.
Server Readiness by Status
Readiness by Application
Server-level assessment showing which systems are ready for lift-and-shift migration and which require remediation or further assessment before deployment.
Application readiness is derived from the status of its associated servers, helping identify low-risk migration candidates and workloads requiring remediation.

## Slide 20
9F8DF1A2-E3F8-4594-8626-CB552ABC3F76
Migration Complexity Assessment
Each application has been assigned a migration complexity score based on factors such as application size, dependency depth, technology stack, infrastructure complexity, and migration treatment. The resulting complexity bands help prioritize migration waves and estimate delivery effort.

## Slide 21
5441D0B0-6355-4EF6-8DD8-95C98A45127E
Migration Wave Plan
An indicative wave plan sequencing workloads by dependency, treatment, and complexity to balance delivery effort across teams.

## Slide 22
F14EAF8A-FA3A-4D8A-A0EB-0DB4311AA6D9
Migration Wave Details
Wave planning groups applications scheduled for migration together based on dependency relationships, migration treatments, complexity, and overall delivery sequencing. The composition and timing of each wave can be refined during detailed migration planning.

## Slide 23
710A8E9C-325B-49F3-8D85-769D77B5AE00
Next Steps & Decision Points
Recommended actions to move from assessment to execution, with clear ownership and decision points for stakeholders.
01
Transition to Continuous Planning
Re-baseline the estate assessment periodically to reflect ongoing changes in the application and infrastructure landscape.
Schedule recurring Dr Migrate reassessments Track changes in application and infrastructure inventory Update stakeholders on estate drift
OUTCOME
Continuously accurate estate visibility
02
Validate & Approve the Migration Strategy
Confirm 6R treatments, wave sequencing, and cost assumptions with business and technical stakeholders before execution begins.
Review treatment decisions with application owners Validate wave grouping and sequencing logic Sign off on cost and effort assumptions
OUTCOME
Approved migration strategy and plan
03
Prepare the Delivery Platform
Stand up the landing zone, migration tooling, and governance model required to support execution at scale.
Finalize landing zone architecture Select and configure migration tooling Define governance and escalation model
OUTCOME
Execution-ready delivery platform
04
Commence Migration Execution
Begin execution of Wave 1, applying lessons learned to refine the approach for subsequent waves.
Kick off Wave 1 migration activities Monitor progress against plan Capture lessons learned for future waves
OUTCOME
Migration underway with continuous feedback

## Slide 24
BAA38C2E-D27E-4808-B525-934523BCBE20
Appendix
Additional insights.

## Slide 25
B1F8D68E-B690-4178-A34C-FFA5D34E2FB5

## Slide 26
14548395-7C62-4AE5-81A8-1C6A4143FCF6
TCO Analysis
>
Scenarios
IaaS Hosting Cost Comparison
Compare projected annual infrastructure costs across Azure hosting, commitment, and right-sizing scenarios to identify the most cost-effective deployment model.

## Slide 27
8ABA3476-A28C-4D40-AA80-9BF6E26DF846
Server Analysis
A high-level summary of the server landscape, including operating system distribution, support status, utilization patterns, and potential opportunities to optimize or decommission underused infrastructure.
Estate Explorer
>
Infrastructure
>
Servers

## Slide 28
A3A496D5-B3E1-4A98-9EDF-A218CE4310F6
Operating System Lifecycle Risk
Identify unsupported operating systems, upcoming end-of-support milestones, and infrastructure requiring remediation to reduce security and operational risk.
Estate Explorer
>
Infrastructure
>
Servers

## Slide 29
7837F4E9-E66C-4EAD-AB7D-3E61D684A20F
VMware Hosting Infrastructure Support
Review the support status of the physical infrastructure hosting your VMware environment. Identify aging hardware, warranty expiry, and end-of-support exposure. Warranty Assumption: Hardware is purchased within 5 years of the release date and with 3 years of warranty. Does not account for if extended warranty was purchased
*Powered down machines do not report make or model.
Estate Explorer
>
Infrastructure
>
Hardware

## Slide 30
FFE4531D-746A-4449-845C-D23F7BC2A134
Security Modernization Opportunities
Identify overlapping security capabilities and consolidate onto modern cloud-native security platforms to simplify operations and reduce cost.
Security Tooling Consolidation
Estate Explorer
>
Technologies
>
Security

## Slide 31
E3AD19DE-EE6A-4B99-8B2C-A1B21BDC721D
Platform & Services Modernization Insights
Platform Services Consolidation Opportunity
Estate Explorer
>
Technologies
>
Platform & Services

## Slide 32
ABAE442C-4B2C-434E-927D-34DB8DBE4FF3
Modern Workplace Modernization Insights
Modern Workplace Consolidation Opportunity
Your workplace environment presents opportunities to consolidate remote access, collaboration, and endpoint management onto cloud services. This reduces platform sprawl while improving security, governance, and the employee experience.
Estate Explorer
>
Technologies
>
Modern Workplace

## Slide 33
7EAE7DAA-1DDD-4F5F-8321-5A45511A9335
Cloud and SaaS Services
Identify opportunities cloud hosting services assessed and initial opportunities

## Slide 34
093D2011-2D75-4C0A-B36D-0A1CDB9CE27E
AWS Services and Cost Overview
Gain a clear view of your AWS landscape, including discovered services, resources distribution and estimated spend across your environment.
AWS Service Inventory Review the services discovered across connected AWS accounts, including resource inventory, service categories, regional distribution, and estimated cloud expenditure.
Estate Explorer
>
Infrastructure
>
AWS

## Slide 35
0DC523BE-5456-4982-8A50-776D755809DD